## Sheet1
Developed by the Community Research, Evaluation, and Development (CRED) Team |  | Enter final submission deadline into the green box
| Sponsor submission deadline:__ | 2024-08-01
2024-08-01
| What? | When?
| 1. 2-3 months prior to the submission deadline- | 2024-05-09
In one or two (long) meetings with the core project team:
- Outline your project concept, including: Situation statement/community need and target population (and any supporting literature/data) Short- and long-term outcomes you hope to achieve, and how you will measure your impact (evaluation) Proposed activities, partners, roles and responsibilities Your team's expertise/edge Project sustainability
-Complete a logic model.
- Then, work through a more detailed project timeline table (e.g., grant quarter- activities- responsible partner- objective fulfilled). Note any details that need to be worked out, and make a plan to resolve these questions.
- Translate the RFP into proposal narrative sections in a shared document (working on Box online) and set writing responsibilities and due dates.
Engage your resources:
-Notify CALES of your intent to apply.
-Set a date to submit a complete draft to RII/ RDS for review (resdev@arizona.edu). The review date should be at least 5 weeks before submission deadline.
-Get in touch with CRED if you would like proposal support (including facilitating the steps above), evaluation consultation, or to include CRED as the evaluator on the grant (CRED@arizona.edu, submit a request for evaluation assistance: https://uarizona.co1.qualtrics.com/jfe/form/SV_6DnxlmMkUT1tcrA)
| 2. First draft completed | 2024-06-13
- Begin "pink team" review:
- Review the full draft for cohesion- do the sections work together? Is there anything that needs more explanation, reordering, or are there redundant sections?
- Review draft against RFP- are any sections missing? How well does it address the prompts?
| 3. "Pink team" review completed; submit draft to RII for review | 2024-06-27
| 4a. Submit agency funding opportunity announcement and budget outline to grant support staff person | 2024-07-11
4b. Begin "red team" review
- Address RII comments and work on strengthening any weak areas of the proposal (e.g., more supporting data)
| 5a. Submit the following to grant support staff: | 2024-07-22
- Project Title
- Project start and end dates
- Project abstract/summary
- Budget and funal documents for any subawards
- Budget justification
- PI/Co-I distribution of credit and F&A
5b. Begin "gold team" review
- Critically review for use of acronyms, terminology, figures and tables, formatting, spelling and grammar, etc.
| 6. Submit completed grant proposal package with all approvals to Sponsored Project Services. | 2024-07-29
*Due date may need to be manually adjusted- 3 business days prior to final submission deadline